## Sheet1
Title | Body | Assignee | Labels | Status | TargetDueDate | Epic
[FEATURE] Helix - Agentic Delivery Introduction | Deliverable - Website |  |  | In Progress |  | Helix - Framework Tasks
[FEATURE] Helix - Agentic Delivery Framework | Deliverable - Website / PPT |  |  | In Progress |  | Helix - Framework Tasks
[FEATURE] Helix - Discovery - Assess Readiness | [5 empty] | Helix - Framework Tasks
Helix - PM Domain discovery (include domain expert discovery) | Deliverable - Workshopt Templates (pain points, scoping, requirements) | John Connolly |  | In Progress | 2026-04-03 | Helix - Framework Tasks
Helix - Define User Acceptance Criteria | Deliverable - Document |  |  | In Progress | 2026-04-03 | Helix - Framework Tasks
[FEATURE] Helix - Design | This milestone establishes the foundational understanding of the business domain and translates it into a structured, agent‑ready software design. It focuses on deep discovery, domain modeling, and creating the architectural blueprint that will guide all downstream agentic development. |  |  |  |  | Helix - Framework Tasks
Helix - PM EventStorming - Big Picture | Deliverable - Lucid Chart | JC |  | In Progress | 2026-03-30 | Helix - Framework Tasks
Helix - PM EventStorming - Process Modeling | Deliverable - Lucid Chart | JC |  | In Progress | 2026-03-30 | Helix - Framework Tasks
Helix - PM Context mapping | Deliverable - Lucid Chart | JC |  | In Progress | 2026-03-30 | Helix - Framework Tasks
Helix - PM EventStorming - Software Design | Deliverable - Lucid Chart | JC, KC |  | Backlog | 2026-03-30 | Helix - Framework Tasks
Helix - PM Design per context | Deliverable - Figma | KC |  | Backlog | 2026-04-10 | Helix - Framework Tasks
Helix - PM Database Design per context | Deliverable - SQL | Nasir |  | Backlog | 2026-04-10 | Helix - Framework Tasks
[FEATURE] Helix - Design to Develop contract | This milestone formalizes the handoff between design and development by producing structured, machine‑readable assets that agentic developers can consume. |  |  |  |  | Helix - Framework Tasks
Helix - Design Software Design CSV | Deliverable - CSV | JC, KC |  | In Progress | 2026-04-07 | Helix - Framework Tasks
Helix - Design Markdown template | Deliverable - MD | JC, KC |  | In Progress | 2026-04-07 | Helix - Framework Tasks
Helix - Design Prompt | Deliverable - txt |  |  | In Progress | 2026-04-07 | Helix - Framework Tasks
Helix - Design UI Assets | Deliverable - Figma |  |  | Backlog | 2026-04-14 | Helix - Framework Tasks
Helix - Design Database Scripts | Deliverable - SQL | Nasir |  | Backlog | 2026-04-14 | Helix - Framework Tasks
[FEATURE] Helix - Client Agentic Enablement (Optional) | This milestone prepares the client’s engineering team to work effectively with agentic workflows and tools. |  |  |  |  | Helix - Framework Tasks
Helix - Setup Client Developers | Deliverable - Document; People Enablement |  |  | Backlog | 2026-04-14 | Helix - Framework Tasks
[FEATURE] Helix - Develop | This milestone executes the agent‑driven development process, combining automated generation with human‑in‑the‑loop oversight. |  |  |  |  | Helix - Framework Tasks
Helix - Design Architectural Instructions | Deliverable - MD | DD, Steve |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Agentic Infrastructure Setup | Deliverable - Agents, settings | KC, Nasir |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Agentic Development (includes data/UI/LLMs) | Deliverable - Code files | KC, Nasir |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Agentic Testing / troubleshooting | Deliverable - Code files | ?? |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Agentic Pull Requests | Deliverable - GitHub | KC |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Agentic Integration Contracts between contexts | Deliverable - Code files |  |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM Telemetry - Application |  |  |  | Backlog |  | Helix - Framework Tasks
[FEATURE] Helix - Develop to Deliver contract | This milestone defines the operational and deployment‑ready assets required to move the solution into delivery. | JC/KC/DD |  | Backlog | 2026-04-10 | Helix - Framework Tasks
[FEATURE] Helix - Deliver | This milestone operationalizes the solution, ensuring it is deployed, validated, and ready for production use. |  |  | In Progress |  | Helix - Framework Tasks
Helix - PM Environment Provisioning | GitHub | DD |  | In Progress | 2026-04-10 | Helix - Framework Tasks
Helix - PM Application deployment | GitHub | DD |  | Backlog | 2026-04-10 | Helix - Framework Tasks
Helix - PM Observability | ?? |  |  | In Progress | 2026-04-14 | Helix - Framework Tasks
Helix - PM QA/ Validation | GitHub | DD |  | Backlog | 2026-04-10 | Helix - Framework Tasks
Helix - Design UAT |  |  |  | In Progress |  | Helix - Framework Tasks
Helix - PM Final Deliverable to Prod |  |  |  | Backlog |  | Helix - Framework Tasks

## Sheet2
Team Member | GitHub Account
Waress Karimi | wkais
KC Jones-Evans | kcjonesevans
Steven Suing | steven-suing
John Connolly | AIS-John-Connolly
Mandy Kaur | Mkblip
Nasir Mirza | nasirmirzagit
JC | AIS-John-Connolly
DD | dracman65